| Phase | Step | Tools/ Techniques | Roles Involved | Deliverables | Gates | Comment |
| --- | --- | --- | --- | --- | --- | --- |
| Organization Strategy | Performing this phase is not part of a project, it is an Organizational activity |  | Executive Management | documented vision mission objectives strategy how to implement the strategy |  | e.g. annual |
| Process Architecture | Performing this phase is not part of a project, it is an Organizational activity | Enterprise Architecture | Enterprise Architecture Group Executive management | Documented and agreed process guidelines Document and agreed Benefits Management Framework Organization corporate Process View, including ARIS Modelling Hierarchy Process Matrices |  | e.g. annual |
| Launch Pad | Communications | Communication Planning Change Management | Project Manager assign change manager | Initial Communications Strategy | Stop immediately unless: the project is funded sufficiently Resolve or determine impact of: an ill-defined or not clear project scope project scope is not finally agreed |  |
|  | Initial key stakeholder interviews | Understand key business drivers and “what is keeping them awake at night” | Project Manager or senior project member | Information that will be important in prioritization and project direction |  |  |
|  | High-Level Process Walk Through | Observation/ Interviews asking questions until you gain an understanding of how the processes work in practice | Process Analyst | Documented high level process overview |  | Can be omitted, if the High Level process is well known to the Process Analyst |
|  | Stakeholder Identification & Engagement | Stakeholder Identification Meetings | Project Manager Process Analyst | List of Stakeholders |  |  |
|  | Executive (Management) Workshop | End-to-End Process Thinking Project Width Process Selection Matrix Process Metrics Red Wine Test Facilitation | Project Manager Process Analyst | Agreed Process Goals Process selection matrix with initial metrics Prioritised Processes |  |  |
|  | Develop Implementation Plan | Implementation Planning | Project Manager Project Sponsor | Initial Implementation Plan |  |  |
|  | Develop & Sign-off Business Case | Cost/Benefit Analysis | Project Manager Project Sponsor | Initial Business Case |  |  |
|  | Define & Establish Project Team Structure | Project Management | Project Manager | Established Project Team |  |  |
|  | Agree & plan handover to business | Involve appropriate business staff in the entire project | Project Manager Project Sponsor Business Owner | Business staff involved in entire project who will be responsible for the processes after project completion |  |  |
|  | Complete Initial Project Plan | Project Planning | Project Manager | Initial Project Plan |  |  |
|  | General Project Management | Project Management | Project Manager | Project Charter document Project Scope document Initial risk analysis |  |  |
| Understand | Communications | Change Management | Project Manager Change Manager | Informed people | Stop immediately unless: Processes are reviewed on a genuine end-to-end basis have the correct business people in the workshops sufficient metrics are gathered else baseline is difficult or impossible to determine future improvement benefits comparison impacted |  |
|  | Understand Workshops | Process Modeling Facilitation skills Workshop Preparation Workshop Facilitation | Process Analyst Business Subject Matter Experts | Process models of current process (in process modelling tool) |  | Only as much as needed |
|  | Metrics Analysis | Data Analysis | Process Analyst | Metrics for baseline & prioritization |  |  |
|  | Root Cause Analysis | Fishbone 5 Whys? | Process Analyst | Understanding of the processes & Root Causes |  |  |
|  | People Capabilities | People Capability Matrix | Process Analyst | Current people capability matrix |  |  |
|  | Identify Available Information | Knowledge & Information Needs Map | Process Analyst | Knowledge & Information Needs Map |  | Identification of available documentation for training & knowledge perpetuation |
|  | Identify Innovate Priorities | Prioritisation | Process Analyst Project Manager | Priorities for Innovate Phase |  |  |
|  | Identify Quick Win Opportunities | Prioritisation | Process Analyst Project Manager | List of Quick Wins |  |  |
|  | Understand Phase Report | Report Writing | Responsibility: Project Manager Executing: eg. Process Analyst | Report for Understand phase |  | Only if necessary Brief report to document findings |
| Innovate | Communications | Change Management Communications Plan | Change Manager All members of the project team | Informed people | Stop immediately unless: the organization has a vision for the Innovate phase and is able to establish process goals, nor determine the scenarios for the phase |  |
|  | Management Kick-Off workshop | Facilitation | Project Manager Project Sponsor | Opportunities & constraints defined by management |  |  |
|  | External Stakeholder Focus Group | Interviewing Facilitation | Process Analyst Project Manager | Documented stakeholder requirements |  | If business thinks this is useful |
|  | Innovate Workshops | Facilitation Creative Thinking Process Design Principles | Process Analyst Facilitator (this could range from the Project Manager, Team Leader or Process Analyst). | Redesigned Process Models |  |  |
|  | Future Process Metrics Projections | Data Analysis Excel Spreadsheet | Process Analyst | Estimated future metrics |  |  |
|  | Simulation | Process modelling & simulation tool | Process Analyst | Simulated process models via selected scenarios |  | Only complete if necessary & has a specific purpose |
|  | Create Initial People Change Management Strategy | Initial People Change Management Strategy report | Human Resources Project Manager | Strategy document |  | Could significantly influence people capability matrix |
|  | Update People Capability Matrix | People Capability Matrix | Process Analyst | Documented gap in capabilities & skills |  |  |
|  | Capacity Planning | Capacity planning tools | Process Analyst | Capacity Planning document |  | Will assist in providing input into performance measures & skills mix |
|  | Workshop Proposed solutions | Baseline Comparison | Process Analyst Project Manager | Sign-Off from Audit, Risk & Compliance, IT |  |  |
|  | Demonstrate & validate feasibility of proposed solution processes | Knowledge of IT systems; risk management; compliance requirements | Project Manager IT staff | Demonstrate feasibility of solution |  |  |
|  | Process gap analysis | Gap Analysis | Process Analyst | Documented gap |  |  |
|  | Update Business Case with Benefits & Obtain Sign-off | Cost/ Benefit Analysis | Project Manager | Refined Business Case |  |  |
|  | Report & presentations | Report template | Project Manager Project Sponsor | Report |  |  |
|  | Business Requirements | Business Analysis Documentation writing skills | Business Analyst Process Analyst | Business Requirements |  |  |
| People | Communications | Change Management Communication Plan | Change Manager All members of the project team | Informed people | Stop immediately unless: staff performance targets are realistic (business unit not understaffed) people being consulted or engaged in the performance measurement establishment Resolve or determine impact of: HR not engaged early enough or at all judging the performance of people within the organization before the process and structural issues have been addressed |  |
|  | Design people strategy | Knowledge of working environment e.g. employee union issues | Project Manager | Strategy document |  | This relates to organization structure change options & approach |
|  | Activity definition | Activity, job & structure analysis RASCI for Role Design | Project Manager Process Analyst | Suggested role definitions |  |  |
|  | Role design | RASCI for Role Design | Project Manager Process Analyst Human Resources Management | New role definitions |  |  |
|  | Performance Management & Measurement | Performance Management | Process Analyst Management HR | Integrated & aligned performance management |  |  |
|  | People Capability Gap Analysis | People Capability Matrix | Process Analyst HR | Capability gaps & action plan |  |  |
|  | Design organizational structure | New roles descriptions Organization structure matrices | Project Manager Process Analyst Human Resources Management | New organization structure |  |  |
|  | Update People Change Management Strategy | Previous strategy document | Project Manager | Updated strategy document |  |  |
|  | Update HR Policies | RASCI for Role Design | Process Analyst with HR Consultant | Updated organization structure, role descriptions & HR policies |  | If appropriate |
|  | Develop Training | Training needs analysis Training development | Training Consultant Process Analyst | Training plan & Training material |  |  |
| Develop | Communication | Change Management Communication Management | Change Manager all project staff | Informed people | Stop immediately unless: Business fully understand what will be delivered. This does not mean that the business has ONLY signed off on specifications Resolve or determine impact of: UAT has not been developed by business & fully communicated to developers |  |
|  | Update functional & technical specifications | Previous specifications | Process Analyst IT staff | Revised functional & technical specifications |  |  |
|  | Software Development | e.g. SDLC, RAD | Business Analysts, Developers, Test Analysts, … | high-level overview of the solution detailed business requirements finalize software selection documentation software specification/design software development/configuration software test scripts and results hardware specification hardware availability hardware test scripts and results integration test scripts and results |  | According to organizations approach |
|  | Testing | System testing strategy, plan and scripts | Process analyst IT staff | Bug free developed software |  |  |
| Implement | Communication | Change Management Communication Management | Change Manager all project team members | informed & motivated people within the organization | Stop immediately unless: Business Testing and/or Training as a show-stoppers has been resolved the business has sufficient expertise or resources to complete User Acceptance Testing Resolve or determine impact of: the core project team is unable to deal with all the enquiries and problems at the start of the implementation and during the early stages |  |
|  | Update Implementation Plan | Implementation Planning Scenarios | Project Manager | finalized implementation plan |  |  |
|  | Testing | Testing | Test Analyst Process Analyst to focus on facilitating the business users to carry out the testing itself Business Users | test cases & results tested & updated systems |  |  |
|  | Train Staff | Training | Training Consultant | trained staff, enabled to work on the new process |  |  |
|  | Mentor Staff | Mentoring & Coaching | Change Manager Project Team Super Users |  |  |  |
|  | Rollout changes; monitor & adjust |  | Project Manager | rolled out solution (updated after testing) which contributes towards addressing the project objectives |  |  |
| Realize Value | Communications | change management | Change Manager Project Manager |  | Stop immediately unless: development strategy does not deliver benefits implementation strategy does not deliver benefits stakeholder analysis understanding magnitude of change organization’s capacity to change organization’s acceptance of BPM Technical Review |  |
|  | Benefits Management Framework (Proc. Arch) | Benefit Management Framework | Process Governance Committee | Benefits Management Framework |  |  |
|  | Identify Potential Benefits & Plan (Launch Pad) | Benefit Summary Plan | Project Manager Change Manager | Benefit Realization Register Benefit summary plan |  |  |
|  | Establish Baseline & Comparative Measurement (Understand) | Data Analysis | Project Manager Change Manager | Baseline Measures |  |  |
|  | Refine & Optimise Benefits Mix (Innovate) | Benefit Milestone Matrix | Project Manager Change Manager |  |  |  |
|  | Define Benefit Details (People, Develop & Implement) | Benefit Delivery Matrix | Project Manager Change Manager | Benefits Delivery Matrix |  |  |
|  | Benefits Delivery & Tracking (Realize Benefit) | Benefit Delivery Matrix | Project Manager Change Manager | Benefits Delivery Matrix |  |  |
|  | Value Monitoring & Maximisation (Sustainable Performance) | Benefit Realisation | Benefit Owner Project Sponsor | Delivery of Results |  |  |
| Sustainable Performance | Communications | Communication management | Change Manager Benefit Owner |  |  |  |
|  | Evaluate Project Results | Baseline Comparison | Project Manager Benefit Owner |  |  |  |
|  | Develop Fine-Tune Sustainability | Process Governance | Project Manager Benefit Owner |  |  |  |
|  | Embed performance measures in management | Information from previous phase & steps Management KPIs | Project Sponsor Project Manager Executive management Business managers | Agree, documented & implemented performance measures e.g. KPIs |  |  |
|  | Introduce feedback loops | Feedback loops Feedforward loops | Project Sponsor Project Manager Business managers | Systems to support the loops |  |  |
|  | Embed Sustainability | Publication of processes | Project Manager Benefit Owner |  |  |  |
|  | Monitor Sustainability | Process performance measurement | Benefit Owner |  |  |  |
|  | Continuous Improvement | Process Governance: Process Stewards (Owners) | Benefit Owner (Process Analyst) | Documented & agreed roles & responsibilities for processes & their management |  |  |